## Wk_06.27.05
PRAM Doc Updated: 20050717
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
PRAM Doc Updated: 20050630
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | [8 empty] | 2005-06-27: TT01
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | [8 empty] | 2005-06-27: TT02
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | [8 empty] | 2005-06-27: TT03
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | [8 empty] | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | [8 empty] | 2005-06-27: TT05
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | [8 empty] | 2005-06-27: TT06
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | [8 empty] | 2005-06-27: TT07
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | [8 empty] | 2005-06-27: TT08
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | [8 empty] | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | [8 empty] | 2005-06-27: TT10
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel.
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path.
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Identified Project Risks. 2.-Created Project Risk Analysis and Management Data Sheet Comments: 1. 2. | [9 empty] | 2005-06-27: Implemented

## Wk_07.04.05
PRAM Doc Updated: 20050709
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | P/F | S/P/Q | 2 | 1 | 1 | 1 | 1 | 6 | 2005-06-27: TT01; 2005-07-04: TT01
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | P | C/P | 2 | 1 | 3 | 3 | 3 | 12 | 2005-06-27: TT02; 2005-07-04: TT08
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | P | S/P | 3 | 2 | 3 | 3 | 3 | 14 | 2005-06-27: TT03
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | P | C/S | 3 | 3 | 3 | 3 | 3 | 15 | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | S/P | C/S/PQ | 1 | 1 | 1 | 2 | 2 | 7 | 2005-06-27: TT05; 2005-07-04: TT02
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | P | S | 2 | 1 | 1 | 1 | 2 | 7 | 2005-06-27: TT06; 2005-07-04: TT03
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | P | P/Q | 2 | 2 | 2 | 3 | 3 | 12 | 2005-06-27: TT07; 2005-07-04: TT09
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | P | P | 2 | 3 | 3 | 2 | 3 | 13 | 2005-06-27: TT08
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | P | P | 3 | 3 | 4 | 3 | 3 | 16 | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | P | C/S/P/Q | 1 | 2 | 2 | 2 | 2 | 9 | 2005-06-27: TT10; 2005-07-04: TT04
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions | S/P | C | 3 | 3 | 2 | 3 | 3 | 14
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms | S/P | S/P/Q | 2 | 2 | 2 | 3 | 3 | 12 | 2005-07-04: TT10
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel. | S/P/R | C/P | 1 | 2 | 2 | 3 | 2 | 10 | 2005-07-04: TT05
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path | S/P/R | P/Q | 2 | 3 | 2 | 3 | 3 | 13
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path. | S/P | P | 2 | 2 | 2 | 3 | 2 | 11 | 2005-07-04: TT06
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation | S/P | P/Q | 3 | 3 | 2 | 3 | 3 | 14
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments | P | P | 2 | 2 | 2 | 3 | 2 | 11 | 2005-07-04: TT07
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Performed Risk Analysis and Mitigation and documented results for week 07/04/05. 2.- Comments: 1.- 2.- | [9 empty] | 2005-06-27: Implemented

## Wk_07.11.05
PRAM Doc Updated: 20050717
PRAM Doc Updated: 20050717
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team | McNAV Team | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | P/F | S/P/Q | 2 | 3 | 3 | 3 | 3 | 14 | 2005-06-27: TT01; 2005-07-04: TT01
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | P | C/P | 2 | 1 | 1 | 1 | 2 | 7 | 2005-06-27: TT02; 2005-07-04: TT08; 2005-07-11: TT02
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | P | S/P | 1 | 2 | 1 | 1 | 1 | 6 | 2005-06-27: TT03; 2005-07-11: TT01
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | P | C/S | 3 | 3 | 3 | 3 | 3 | 15 | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | S/P | C/S/PQ | 2 | 2 | 2 | 2 | 2 | 10 | 2005-06-27: TT05; 2005-07-04: TT02; 2005-07-11: TT06
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | P | S | 2 | 1 | 1 | 1 | 2 | 7 | 2005-06-27: TT06; 2005-07-04: TT03; 2005-07-11: TT03
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | P | P/Q | 1 | 2 | 2 | 2 | 2 | 9 | 2005-06-27: TT07; 2005-07-04: TT09; 2005-07-11: TT05
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | P | P | 2 | 3 | 2 | 2 | 2 | 11 | 2005-06-27: TT08; 2005-07-11: TT07
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | P | P | 3 | 3 | 4 | 3 | 3 | 16 | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | P | C/S/P/Q | 3 | 2 | 3 | 3 | 3 | 14 | 2005-06-27: TT10; 2005-07-04: TT04
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions | S/P | C | 3 | 3 | 2 | 3 | 3 | 14
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms | S/P | S/P/Q | 2 | 1 | 2 | 2 | 1 | 8 | 2005-07-04: TT10; 2005-07-11: TT04
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel. | S/P/R | C/P | 2 | 3 | 3 | 3 | 3 | 14 | 2005-07-04: TT05
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path | S/P/R | P/Q | 2 | 3 | 3 | 3 | 3 | 14
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path. | S/P | P | 2 | 2 | 2 | 3 | 2 | 11 | 2005-07-04: TT06; 2005-07-11: TT08
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation | S/P | P/Q | 2 | 3 | 2 | 2 | 3 | 12 | 2005-07-11: TT09
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments | P | P | 2 | 3 | 2 | 3 | 3 | 13 | 2005-07-04: TT07; 2005-07-11: TT10
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Performed Risk Analysis and Mitigation and documented results for week 07/11/05. 2.- Comments: 1.- 2.- | [9 empty] | 2005-06-27: Implemented

## Wk_07.18.05
PRAM Doc Updated: 20050721
PRAM Doc Updated: 20050721
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team | McNAV Team | McNAV Team | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | P/F | S/P/Q | 2 | 1 | 1 | 1 | 1 | 6 | 2005-06-27: TT01; 2005-07-04: TT01; 2005-07-18: TT01
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | P | C/P | 2 | 1 | 3 | 3 | 3 | 12 | 2005-06-27: TT02; 2005-07-04: TT08; 2005-07-11: TT02; 2005-07-18: TT09
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | P | S/P | 3 | 2 | 3 | 3 | 3 | 14 | 2005-06-27: TT03; 2005-07-11: TT01
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | P | C/S | 3 | 3 | 3 | 3 | 3 | 15 | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | S/P | C/S/PQ | 2 | 2 | 2 | 3 | 2 | 11 | 2005-06-27: TT05; 2005-07-04: TT02; 2005-07-11: TT06; 2005-07-18: TT06
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | P | S | 2 | 1 | 2 | 1 | 2 | 8 | 2005-06-27: TT06; 2005-07-04: TT03; 2005-07-11: TT03; 2005-07-18: TT03
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | P | P/Q | 2 | 2 | 2 | 3 | 3 | 12 | 2005-06-27: TT07; 2005-07-04: TT09; 2005-07-11: TT05; 2005-07-18: TT08
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | P | P | 2 | 3 | 3 | 2 | 3 | 13 | 2005-06-27: TT08; 2005-07-11: TT07
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | P | P | 3 | 3 | 4 | 3 | 3 | 16 | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | P | C/S/P/Q | 1 | 2 | 2 | 3 | 2 | 10 | 2005-06-27: TT10; 2005-07-04: TT04; 2005-07-18: TT05
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions | S/P | C | 3 | 3 | 2 | 3 | 3 | 14
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms | S/P | S/P/Q | 2 | 2 | 2 | 3 | 3 | 12 | 2005-07-04: TT10; 2005-07-11: TT04
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel. | S/P/R | C/P | 1 | 1 | 1 | 2 | 2 | 7 | 2005-07-04: TT05; 2005-07-18: TT02
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path | S/P/R | P/Q | 2 | 3 | 2 | 3 | 3 | 13 | 2005-07-18: TT10
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path. | S/P | P | 1 | 2 | 2 | 2 | 2 | 9 | 2005-07-04: TT06; 2005-07-11: TT08; 2005-07-18: TT04
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation | S/P | P/Q | 3 | 3 | 2 | 3 | 3 | 14 | 2005-07-11: TT09
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments | P | P | 2 | 2 | 2 | 3 | 2 | 11 | 2005-07-04: TT07; 2005-07-11: TT10; 2005-07-18: TT07
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Performed Risk Analysis and Mitigation and documented results for week 07/11/05. 2.- Comments: 1.- 2.- | [9 empty] | 2005-06-27: Implemented
| 2005-07-22 | Ghislaine | 1.-Changed PRAM-07 from TT09 to TT10 for 7/4/2005 since there were 2 risks marked with TT09 (PRAM-12 was also). 2.-Filled out Risks prioritization for 0718/2005 based on knowledge from the updates from other documents released from the team Comments: 1.-I believe PRAM-10 and PRAM-03 could be consolidated to one Risk 2.-I think PRAM-16 and PRAM-05 could be consolidated to one Risk Discussion: 1.-I belive that the Impact and Consequence of both PRAM-03 and PRAM-10 is similar but for different reasons. 2.-I belive that the Impact and Consequence of both PRAM-05 and PRAM-16 is similar but for different reasons - temperature probably due to radiation and must be appropriately addressed with efficient cooling system. And Radiation which will require a different solution in terms of an effective shielding system. | [9 empty] | 2005-06-27: Implemented

## Wk_07.25.05
PRAM Doc Updated: 20050721
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | P/F | S/P/Q | 1 | 1 | 1 | 1 | 1 | 5 | TT01 | TT01 | TT01 | TT01 | TT01
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | P | C/P | 2 | 1 | 3 | 3 | 3 | 12 | TT02 | TT08 | TT09 | TT09 | TT08
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | P | S/P | 1 | 1 | 1 | 2 | 1 | 6 | 2005-06-27: TT03; 2005-07-25: TT02
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | P | C/S | 3 | 3 | 3 | 3 | 3 | 15 | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | S/P | C/S/PQ | 1 | 2 | 2 | 2 | 2 | 9 | TT05 | TT02 | TT06 | TT06 | TT05
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | P | S | 2 | 1 | 1 | 1 | 2 | 7 | TT06 | TT03 | TT03 | TT03 | TT03
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | P | P/Q | 1 | 2 | 2 | 2 | 3 | 10 | TT07 | TT10 | TT08 | TT08 | TT06
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | P | P | 2 | 3 | 3 | 2 | 3 | 13 | 2005-06-27: TT08
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | P | P | 3 | 3 | 4 | 3 | 3 | 16 | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | P | C/S/P/Q | 1 | 2 | 2 | 2 | 2 | 9 | 2005-06-27: TT10; 2005-07-04: TT04; 2005-07-11: TT05; 2005-07-18: TT05
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions | S/P | C | 3 | 3 | 2 | 3 | 3 | 14
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms | S/P | S/P/Q | 3 | 3 | 2 | 3 | 3 | 14 | 2005-07-04: TT09
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel. | S/P/R | C/P | 2 | 2 | 2 | 3 | 2 | 11 | 2005-07-04: TT05; 2005-07-11: TT02; 2005-07-18: TT02; 2005-07-25: TT07
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path | S/P/R | P/Q | 2 | 3 | 3 | 3 | 3 | 14 | 2005-07-11: TT10; 2005-07-18: TT10
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path. | S/P | P | 2 | 3 | 2 | 3 | 3 | 13 | 2005-07-04: TT06; 2005-07-11: TT04; 2005-07-18: TT04; 2005-07-25: TT10
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation | S/P | P/Q | 1 | 1 | 1 | 3 | 2 | 8 | 2005-07-25: TT04
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments | P | P | 2 | 2 | 2 | 3 | 3 | 12 | 2005-07-04: TT07; 2005-07-11: TT07; 2005-07-18: TT07; 2005-07-25: TT09
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Performed Risk Analysis and Mitigation and documented results for week 07/11/05. 2.- Comments: 1.- 2.- | [9 empty] | 2005-06-27: Implemented
| 2005-07-22 | Ghislaine | 1.-Changed PRAM-07 from TT09 to TT10 for 7/4/2005 since there were 2 risks marked with TT09 (PRAM-12 was also). 2.-Filled out Risks prioritization for 0718/2005 based on knowledge from the updates from other documents released from the team Comments: 1.-I believe PRAM-10 and PRAM-03 could be consolidated to one Risk 2.-I think PRAM-16 and PRAM-05 could be consolidated to one Risk Discussion: 1.-I belive that the Impact and Consequence of both PRAM-03 and PRAM-10 is similar but for different reasons. 2.-I belive that the Impact and Consequence of both PRAM-05 and PRAM-16 is similar but for different reasons - temperature probably due to radiation and must be appropriately addressed with efficient cooling system. And Radiation which will require a different solution in terms of an effective shielding system. | [9 empty] | 2005-06-27: Implemented

## 08.01.05
PRAM Doc Updated: 20050721
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | P/F | S/P/Q | 2 | 1 | 1 | 1 | 2 | 7 | TT01 | TT01 | TT01 | TT01 | TT01 | TT03
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | P | C/P | 2 | 1 | 3 | 3 | 3 | 12 | TT02 | TT08 | TT09 | TT09 | TT08 | TT10
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | P | S/P | 1 | 1 | 2 | 3 | 2 | 9 | 2005-06-27: TT03; 2005-07-25: TT02; 2005-08-01: TT06
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | P | C/S | 3 | 3 | 3 | 3 | 3 | 15 | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | S/P | C/S/PQ | 1 | 1 | 1 | 2 | 2 | 7 | TT05 | TT02 | TT06 | TT06 | TT05 | TT02
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | P | S | 2 | 1 | 2 | 1 | 2 | 8 | TT06 | TT03 | TT03 | TT03 | TT03 | TT05
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | P | P/Q | 2 | 2 | 2 | 3 | 3 | 12 | TT07 | TT10 | TT08 | TT08 | TT06 | TT09
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | P | P | 2 | 3 | 3 | 2 | 3 | 13 | 2005-06-27: TT08
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | P | P | 3 | 3 | 4 | 3 | 3 | 16 | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | P | C/S/P/Q | 1 | 2 | 2 | 2 | 2 | 9 | 2005-06-27: TT10; 2005-07-04: TT04; 2005-07-11: TT05; 2005-07-18: TT05
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions | S/P | C | 3 | 3 | 2 | 3 | 3 | 14
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms | S/P | S/P/Q | 1 | 2 | 2 | 3 | 2 | 10 | 2005-07-04: TT09; 2005-08-01: TT08
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel. | S/P/R | C/P | 1 | 2 | 2 | 3 | 2 | 10 | 2005-07-04: TT05; 2005-07-11: TT02; 2005-07-18: TT02; 2005-07-25: TT07
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path | S/P/R | P/Q | 2 | 3 | 2 | 3 | 3 | 13 | 2005-07-11: TT10; 2005-07-18: TT10
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path. | S/P | P | 1 | 1 | 2 | 2 | 2 | 8 |  | TT06 | TT04 | TT04 | TT10 | TT04
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation | S/P | P/Q | 1 | 1 | 1 | 2 | 1 | 6 | 2005-07-25: TT04; 2005-08-01: TT01
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments | P | P | 1 | 1 | 2 | 3 | 2 | 9 |  | TT07 | TT07 | TT07 | TT09 | TT07
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Performed Risk Analysis and Mitigation and documented results for week 07/11/05. 2.- Comments: 1.- 2.- | [9 empty] | 2005-06-27: Implemented
| 2005-07-22 | Ghislaine | 1.-Changed PRAM-07 from TT09 to TT10 for 7/4/2005 since there were 2 risks marked with TT09 (PRAM-12 was also). 2.-Filled out Risks prioritization for 0718/2005 based on knowledge from the updates from other documents released from the team Comments: 1.-I believe PRAM-10 and PRAM-03 could be consolidated to one Risk 2.-I think PRAM-16 and PRAM-05 could be consolidated to one Risk Discussion: 1.-I belive that the Impact and Consequence of both PRAM-03 and PRAM-10 is similar but for different reasons. 2.-I belive that the Impact and Consequence of both PRAM-05 and PRAM-16 is similar but for different reasons - temperature probably due to radiation and must be appropriately addressed with efficient cooling system. And Radiation which will require a different solution in terms of an effective shielding system. | [9 empty] | 2005-06-27: Implemented

## Wk_08.08.05
PRAM Doc Updated: 20050721
ESIS - Summer 2005: DARPA Lunar Grand Challenge 2005 (MBARS) Project
McNAV Project Risk Analysis & Management (PRAM)
McNAV Team's TOP TEN Project Risks for Week 28/2005
See Doc Change History Below |  | McNAV - Project Risk Classification & Analysis Weight Factor |  |  | Risk Management Roles & Functions | [7 empty] | Risk Prioritization Responsibility
|  | Greater <<<<< 1 ; 2 ; 3 ; 4 >>>>> Lesser |  |  | Identification |  |  |  | McNAV Team |  |  |  | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team | McNAV Team
|  | Group | Safety, Program, Funding, Resources |  | Analysis & Mitigation |  |  |  | McNAV Team
|  | Consequence | Cost, Schedule, Performance, Quality |  | Weekly Priortization |  |  |  | McNAV Team
|  | Impact | {1} Catastrophic, {2} Critical, {3} Marginal, {4} Insignificant |  | DB Management |  |  |  | Gurmit Lotey
|  | Priority | {1} High, {2} Medium, {3} Low, {4} Ultra Low |  | Reporting - DocBoss |  |  |  | Gurmit Lotey
|  | Severity | {1} Critical, {2} Serious, {3} Moderate, {4} Minor
|  | Probability | {1} High [> 70%], {2} Medium [30% < x < 70%], {3} Low [< 30%], {4} Insignificant |  | Group | Consequence | Impact | Priority | Severity | Probability | Timeframe | SCORE
|  | Timeframe | {1} Near-term, {2} Medium-term, {3} Long-term, {4} Out-of-Scope
CMT Risk ID | Entry Date | Risk Description |  | McNAV Team's Mitigation Actions | [8 empty] | Prioritized Top Ten Risks for Week Beginning
[13 empty] | 2005-06-27 | 2005-07-04 | 2005-07-11 | 2005-07-18 | 2005-07-25 | 2005-08-01 | 2005-08-08 | 2005-08-15
PRAM-01 | 2005-06-25 | If adequate funding for the McNAV project is not secured, there is a possibility that the project will not succeed. |  | 1. Launch a fund raising campaign 2. Sell available real estate on vehicle to sponsors 3. Approach Congress for project funding | P/F | S/P/Q | 2 | 1 | 1 | 1 | 1 | 6 | TT01 | TT01 | TT01 | TT01 | TT01 | TT03
PRAM-02 | 2005-06-25 | Since the lunar data is unverified, there is a possibility that McNAV vehicle will not be able to function as designed. |  | 1. Consult with appropriate space agencies and subject matter experts to confirm lunar data. 2. Change McNAV design to reflect lunar data. | P | C/P | 2 | 1 | 3 | 3 | 3 | 12 | TT02 | TT08 | TT09 | TT09 | TT08 | TT10
PRAM-03 | 2005-06-25 | Given the lack of prior experience in Lunar Autonomous Rover Development, there is a possibility that the project will slip schedule and incur budget over runs. |  | 1. Consult independent Subject Matter Experts [SME] during system design, development, and quality control 2. Provide short course training on topics in Team experience weakness | P | S/P | 3 | 2 | 3 | 3 | 3 | 14 | 2005-06-27: TT03; 2005-07-25: TT02; 2005-08-01: TT06
PRAM-04 | 2005-06-25 | Given poor communication amongst McNAV Team members, there is a possibility that the project schedule will slip |  | 1. Improve communication tools 2. Implement communication protocols to improve efficiency 3. Implement collaboration protocols to reduce document exchange confusion | P | C/S | 3 | 3 | 3 | 3 | 3 | 15 | 2005-06-27: TT04
PRAM-05 | 2005-06-25 | Given the lunar temperature extremes, there is a possibility that the McNAV equipment will not work. |  | 1. Perform McNAV component tests in environmental test chambers simulating lunar conditions | S/P | C/S/PQ | 1 | 1 | 1 | 2 | 2 | 7 | TT05 | TT02 | TT06 | TT06 | TT05 | TT02
PRAM-06 | 2005-06-25 | Given the program schedule and insufficient resources, there is a possibility that project will not be completed |  | 1. Launch an early campaign to acquire appropriate levels of resource allocation based on race schedule. | P | S | 2 | 1 | 1 | 1 | 2 | 7 | TT06 | TT03 | TT03 | TT03 | TT03 | TT05
PRAM-07 | 2005-06-25 | Given that there is insufficient power requirement data, there is a possibility that an incorrect power source will be selected |  | 1. Conduct a thorough Trade Study to investigate Peak Power Usage of all components used on McNAV 2. Conduct a thorough investigation of Power Generation Capabilities (PGC) to be deployed. 3. Conduct Power Generation Unit Evaluations under Peak Loads with McNAV components 4. Add an additional 10 % margin to Peak Power Usage to guarantee sufficient power capacity. | P | P/Q | 2 | 2 | 2 | 3 | 3 | 12 | TT07 | TT10 | TT08 | TT08 | TT06 | TT09
PRAM-08 | 2005-06-25 | Given lateral vehicle motion, there is a possibility that the LADAR sensor (on mast) reading accuracy and repeatability will be affected. |  | 1. Create models of vehicle motion affects on sensor accuracy and repeatability 2. Evaluate vehicle motion on sensor data and generate compensation algorithms | P | P | 2 | 3 | 3 | 2 | 3 | 13 | 2005-06-27: TT08
PRAM-09 | 2005-06-25 | Given the LADAR mast fails to telescope out, there is a possibility that the angular resolution will be reduced. |  | 1. Mount the LADAR mast as high as possible onto the vehicle chassis 2. Conduct mast operation tests for reliability 3. Conduct tests to ensure a degraded LADAR resolution is available even with the mast non-operational | P | P | 3 | 3 | 4 | 3 | 3 | 16 | 2005-06-27: TT09
PRAM-10 | 2005-06-25 | Given that it is hard to find previous examples of similar lunar programs, there is a possibility that the McNAV Team will misjudge the scope and difficulty involved with the program. |  | 1. Deploy available SMEs as consultants during all phases of the project – particularly during design and development. | P | C/S/P/Q | 1 | 2 | 2 | 2 | 2 | 9 | 2005-06-27: TT10; 2005-07-04: TT04; 2005-07-11: TT05; 2005-07-18: TT05
PRAM-11 | 2005-06-25 | Given the participation of the McNAV rover in DARPA's Lunar Grand Challenge 2005, there is a possibility that this will result in lunar pollution. |  | 1. Include the requirement that no harmful components dangerous to the lunar environment shall be used in the construction of the vehicle 2. Design self contained components producing zero polluting emissions | S/P | C | 3 | 3 | 2 | 3 | 3 | 14
PRAM-12 | 2005-06-25 | Given the mechanical motion/traction/steering response delay and accuracy, there is a possibility that that will adversely affect the navigation system. |  | 1. Create motion/traction/steering response delay and accuracy models 2. Evaluate the results and generate dynamic compensation algorithms | S/P | S/P/Q | 2 | 2 | 2 | 3 | 3 | 12 | 2005-07-04: TT09; 2005-08-01: TT08
PRAM-13 | 2005-06-25 | Given that there are no references to the existence of complete temperature maps, vector data of the Magellan Path, and elevation models, there is a possibility that the McNAV rover will be damaged. |  | 1. Solicit DARPA for vector data on the intended Magellan paths to be used. 2. Solicit NASA for available unclassified data of the lunar surface and the Magellan path 3. Consult with SMEs for conditions on lunar surface and the Magellan path. 4. Build the MCNAV system to be capable of lunar circumnavigation on an arbitrary path above the 75th parallel. | S/P/R | C/P | 1 | 2 | 2 | 3 | 2 | 10 | 2005-07-04: TT05; 2005-07-11: TT02; 2005-07-18: TT02; 2005-07-25: TT07
PRAM-14 | 2005-06-25 | Given that actual road testing is not possible before launch, there is a possibility that rover will undergo a catastrophic failure. |  | 1. Perform simulation testing of the perception and navigation systems 2. Perform live testing at earth locations similar in terrain to lunar conditions for distances approximating those of the intended Magellan path | S/P/R | P/Q | 2 | 3 | 2 | 3 | 3 | 13 | 2005-07-11: TT10; 2005-07-18: TT10
PRAM-15 | 2005-06-25 | Given that actual lunar conditions may not match available a-priori data, there is a possibility that rover will fail to complete the race. |  | 1. MCNAV system will be capable of sensing its environment and dynamically re-planning a new trajectory based on a combination of best available information. 2. As the lunar rover traverses the lunar surface it will collect and update its available a-priori data with sensed environmental conditions and periodically plan new trajectories as obstacles or other hazards are detected in its path. | S/P | P | 2 | 2 | 2 | 3 | 2 | 11 |  | TT06 | TT04 | TT04 | TT10 | TT04
PRAM-16 | 2005-06-25 | Given the intense solar radiation exposure, there is a possibility that McNAV equipment will be damaged. |  | 1. Use components which are capable of surviving intense solar radiation for the duration of the course 2. Give preference space-ready or militarized sensors and components 3. Provide effective radiation shielding radiation sensitive components 4. Provide pairs of redundant components such that in the event that any one component fails – the system will be capable of completing its mission goal in a degraded mode of operation | S/P | P/Q | 3 | 3 | 2 | 3 | 3 | 14 | 2005-07-25: TT04; 2005-08-01: TT01
PRAM-17 | 2005-06-25 | Given the lack of data for CPU/Processing, there is a possibility that the vehicle will not be able to complete the race. |  | 1. Produce mathematical and simulation models of the completed system 2. Used the models to verify that the processing capacity is sufficient to complete the mission goals under peak CPU loads – such as when operating at full speed or when traveling in densely cluttered environments | P | P | 2 | 2 | 2 | 3 | 2 | 11 |  | TT07 | TT07 | TT07 | TT09 | TT07
PRAM-18
PRAM-19
PRAM-20
PRAM-21
PRAM-22
PRAM-23
PRAM-24
PRAM-25
PRAM-26
PRAM-27
PRAM-28
PRAM-29
PRAM-30
Docoment Change History | bar: 2005-06-27 to 2005-07-11
| Date | Request By | Change Description | [9 empty] | 2005-06-27: Action
| 2005-06-30 | McNAV Team | 1.-Performed Risk Analysis and Mitigation and documented results for week 07/11/05. 2.- Comments: 1.- 2.- | [9 empty] | 2005-06-27: Implemented
| 2005-07-22 | Ghislaine | 1.-Changed PRAM-07 from TT09 to TT10 for 7/4/2005 since there were 2 risks marked with TT09 (PRAM-12 was also). 2.-Filled out Risks prioritization for 0718/2005 based on knowledge from the updates from other documents released from the team Comments: 1.-I believe PRAM-10 and PRAM-03 could be consolidated to one Risk 2.-I think PRAM-16 and PRAM-05 could be consolidated to one Risk Discussion: 1.-I belive that the Impact and Consequence of both PRAM-03 and PRAM-10 is similar but for different reasons. 2.-I belive that the Impact and Consequence of both PRAM-05 and PRAM-16 is similar but for different reasons - temperature probably due to radiation and must be appropriately addressed with efficient cooling system. And Radiation which will require a different solution in terms of an effective shielding system. | [9 empty] | 2005-06-27: Implemented