## Slide 1
Risk Management

## Slide 2: Today’s Agenda
What is risk anyway?
How do we deal with risk?
What is risk management?
What do we do when our system fails?
Can we identify system failures before they occur?
Can we mitigate system failures proactively?

## Slide 3: What is Risk?
Websters 9th defines risk as:
1: possibility of loss or injury - peril
2: a dangerous element or factor
Risk is uncertainty
A Risk  A Problem: A risk is a problem who time has not yet come
  Example: Should I get my umbrella when it is raining or in anticipation of rain?

## Slide 4: What is Risk?
Software Risk: a measure of the probability and severity of adverse effects inherent in the development of a software system that does not meet the intended functions and performance requirements, the result of which may be: decreased quality, increased cost, delays, loss of market share, or catastrophic failure
Is software development a risky endeavor?

## Slide 5: The Software Crisis?
In 1995 the US spent more than $250 billion for software development on 175,000 projects.
  average annual costs for a large company 2.3M
  average annual for a medium company is 1.3M
  average annual for a small company is $434K
Given:
Large Company: > $500 million in revenue
Medium Company: $200 - $500 million in revenue
Small Company: $100 - $200 million in revenue
“Chaos: The Dollar Drain of IT Project Failures”, Application Development Trends, January 1995

## Slide 6: The Software Crisis?
31.1% of projects in all categories were canceled before completion
  Cost: $81 billion
  52.7% will overrun their initial estimates by 189%
  16.2% will complete on time and and within their budget
“Chaos: The Dollar Drain of IT Project Failures”, Application Development Trends, January 1995

## Slide 7: Symptoms of the Crisis
DEVELOPMENT COST OVERRUNS
FAILED SYSTEM
PERFORMANCE
DEVELOPMENT
SCHEDULE OVERRUNS
COSTLY SYSTEMS
TO SUPPORT
“ON SOFTWARE SCHEDULES, WE’VE GOT A PERFECT RECORD...
WE’VE NEVER MADE ONE ON TIME YET!”
GENERAL BERNARD P. RANDOLPH
COMMANDER, AIR FORCE SYSTEMS COMMAND
AIR FORCE ASSOCIATION SYMPOSIUM, JANUARY 1989
SOFTWARE
CRISIS

## Slide 8: General Software Project Risks
Software risks fall into 3 very broad categories
  Programmatic Risks
    cost, schedule
  Product Risks
    technology, features
  Development Environment
    process, work environment, logistics
  Operational Risks
    how gracefully does a system fail

## Slide 9: Software Project Risk
The need to formally manage risk increases with system complexity
System Complexity
Risk
formal risk
management
corporate expertise
expert knowledge,
Judgement, experience
capable individuals

## Slide 10
Risk and Software Lifecycle
Software is developed in 5 general phases
  requirements (gathering and analysis)
  design
  build
  test
  deploy, maintain, decommission
This is the Software Life Cycle
Each phase has unique risks

## Slide 11: Software Lifecycle Models
Two general schools of thought
  “big bang” approach
    the product is delivered all at once
  cyclical approach
    the product is developed and possibly delivered in increments

## Slide 12: Water Fall Model
“Big Bang” development is usually associated with the Waterfall Model
  earliest definition of a software development model (MILSTD 2167)
  technology had some influence on the model
    slow code, compiler, debug cycles
  reflected the way that other engineering disciplines built things
  still popular today

## Slide 13: Water Fall Model
What are the strengths and weaknesses of this model?

## Slide 14: Cyclical Models
There are numerous cyclical models
  incremental
  spiral
  rapid application development (RAD)
Each prescribes building and delivering the system in “inch-stones” rather than “mile-stones”
  developers iteratively build more function into the system

## Slide 15: The Spiral Model
What are the strengths and weaknesses of this model?
determine objectives,
alternative, constraints
identify and resolve
associated risks
develop and verify
product
evaluate and validate
product, plan next cycle

## Slide 16: Software Development Risks
Risk is an inherent part of software development
Personal Experience:
  risk is often ignored or at best dealt with in an ad-hoc way
  risks are not identified proactively
    allowed to become problems before any action is taken

## Slide 17: Where Do Risks Come From?
There are the...
..things we know
..things we know that we don’t know
..things we don’t know that we don’t know
There are even things we don’t want to know... (maybe they will just go away)

## Slide 18: Scope of Control
There are those risk elements that we can control
  internal origin
Other risk elements we cannot control
  external origin
  however since they effect us, we are obligated to plan for them
Any “real-world” project typically has both

## Slide 19: Sources of System Development Risk
All areas of system development are potential sources of software risks
Technology
Cost
Software
Schedule
Hardware
People
System

## Slide 20: Risk Management
The Good News: Risk can be managed
  Involves continuous set of activities to identify, confront, and resolve risks
Analyze
Identify
Plan
Track
Control
Risks

## Slide 21: Risk Management
Identify: Before risks can be managed, they must be identified before they become a problem
Analyze: Analysis is the conversion of risk data into decision-making information
Plan: Developing and documenting risk mitigation strategies that will be enacted given the presence of risk triggers

## Slide 22: Risk Management
Track: Continuous monitoring of stated risk triggers to see if any have occurred.
Control: Continually reviewing risk plans for relevance and modifying them as appropriate to serve the interest of the project
Control
Identify
Analyze
Plan
Track

## Slide 23: When is Risk Addressed?
From the beginning of a project various risk factors will become evident
  requirements elicitation
  requirements analysis
As early as possible we need to identify, document, and manage risks through the development lifecycle
  more risks will surface through the remaining phases

## Slide 24: Software Risk Evaluation (SRE)
The SRE method was developed at the SEI to help organizations manage risks
Contracting
Mitigation Planning
Identification
Analysis
Interim Report
Final Report

## Slide 25: Contracting Phase
Goals:
  selecting participants
  setting stakeholder expectations
  securing sponsorship from management
  agreeing upon deliverables
  establish schedules

## Slide 26: Contracting Phase
Goals (continued):
  obtain a “picture of success”
    when will you be successful?
    what will make you successful?
    how do you measure success?
Outputs:
  plan, schedule for SRE, and vision of success

## Slide 27: Identification and Analysis Phase
Complete Taxonomy Based Questionnaire
Class
Element
Attribute

## Slide 28: Identification and Analysis Phase
Conduct 1 or More Interviews
  three hour brainstorming sessions
    elicit risks within the project and organization
    evaluate probability and impact
    record risk statements
Condition
Consequence
“No simulation of the system’s
performance has been done”
“We may not meet the
performance requirements”

## Slide 29: Identification and Analysis Phase
Artifacts:
  a set of risk statements, pick top ~5 risks
  completed participant evaluation forms
  minutes from interview meetings
Goals:
1. Coverage
2. Quality of Statements
3. Number of Risks
Condition
Consequence

## Slide 30: Interim Report
Forms the basis of the SRE:
  identifies the major risks facing the project
    risk statements
    probabilities
    impact
  presents data as garnered from SRE and project stakeholders
  may also include a presentation

## Slide 31: Interim Report
Sample Outline:
Executive Summary
Introduction
SRE Process Overview
Background
Findings
Conclusions
Appendices
summary of findings and risk areas
near term recommendations
purpose and layout of this report
explains the SRE process briefly to
set context for the reader
SRE objectives, SRE team, other
relevant roles
presentation of project risks and risk
data
next steps
as required

## Slide 32: Risk Exposure Matrix
Catastrophic
Cost
Software
Schedule
Hardware
People
Critical
Marginal
Negligible
Impact
Component
a) Identify Risk
b) Estimate Probability
1 - High
2 - Medium
3 - Low
c) Enter risk
statement and
probability in
matrix
Example Matrix

## Slide 33: Top Ten List
It is nice to include a “short list” of the most critical program risks
Rank Risk Consequences Triggers Mitigation POC
. . .
1
2
:
10
. . .
. . .
. . .
. . .
. . .
. . .
. . .
. . .
. . .

## Slide 34: Mitigation Planning Phase
Goal:
  identify risk triggers
    a trigger is evidence that your exposure to a risk condition has increased
  identify data collection strategies for monitoring risks
  develop mitigation strategies

## Slide 35: Mitigation Planning Phase
Risks are assigned to “owners”
SRE team works with risk owners:
  to find ways to identify various triggers
  develop various strategies to handle triggering situations as soon as they appear
Condition
Consequence
trigger
trigger
trigger

## Slide 36: Final Report
Refinement of Interim Report that includes:
  risk triggers
  risk owners
  risk mitigation strategies
Typically includes a presentation

## Slide 37: Software Failure - not an Option
Operational risks are unavoidable
  what happens when something fails?
  how gracefully will your system fail?

## Slide 38: Software, Hardware, and Safety
It is tempting to use software to replace hardware
  development costs for SW is higher than for HW while reproduction costs for SW are almost zero
Hardware obeys certain physical laws that make some unsafe behaviors impossible
As software becomes more complex, the possibility of failure increases

## Slide 39: Correctness, Reliability, Safety
Correctness has 2 broad components
  functional construction errors
  errors in meeting specification
Reliability - the measure of the rate of failure of a system, including its software component
Safety - the degree in which system functions do not lead to an accident causing loss of life, limb, or property

## Slide 40: Reliability and Safety
Important Point: Reliability does not always imply safety
  a safe system may fail
    safe systems “fail safe”
  an unsafe system may be reliable

## Slide 41: Failure Modes Effects Analysis
The purpose of a FMEA
  anticipate system failures
  ensure that failures are detected
  categorize and prioritize failures
  eliminate or gracefully handle failures
  determine the effect on the system and the impact to system functionality
  ensure that the failure does not cause unacceptable loss

## Slide 42: Background
SW must detect failures and ensure they are handled in a satisfactory way
Function
Failure
Software
Hardware
System
Detection
Controlled
Behavior
Not
Detected
Uncontrolled
Behavior

## Slide 43: FMEA
For many years there has been a number of standards that try to define processes in Failure Mode and Effects Analysis (FMEA)
  originated with hardware systems
  been applied to software
  currently enjoying popularity in systems engineering discipline

## Slide 44: FMEA Standards
Ministry of Defence (UK) MOD 00-55
  procurement of safety critical systems
Ministry of Defence (UK) MOD 00-56
  identify, evaluate, and minimize risk
MIL-STD-1629A
  identify, evaluate, and minimize risk
MIL-STD-882B
  for contracted developers of safety critical systems

## Slide 45: FMEA Standards
MOD 00-31
  safety critical SW for airborne systems
International Energy Commission IEC-880
  nuclear power plant safety
SAE Recommended Practice
  jointly developed by US Automakers
  sponsored by US Council for Automotive Research (USCAR)
  provides guidance in FMEA techniques

## Slide 46
Software FMEA Approaches
Three Broad Approaches
Situational/Scenario Based Approach
  identify a failure situation
  identify system elements contributing to failure
  conduct FMEA analysis based on situations contributing to failure

## Slide 47: Software FMEA Approaches
Three Broad Approaches (continued)
Systems Approach
  component centric
    partition system into components
    analyze component failures
  function centric
    analyze system function failures
Conduct FMEA analysis based on those units where software intersects function or component

## Slide 48
Software FMEA Approaches
Two Broad Approaches (continued)
Software Module Approach
  identify a software modules
  identify module failures
    software inspections serve this purpose well
  conduct FMEA analysis based on those modules and their associated failures

## Slide 49: When do you do a FMEA
FMEA
Requirements
Analysis
Design
Code
Verification
Validation
prevent/remove fault conditions
identify risks to the system
ensure that designs adequately
handle potential faults
ensure that the system behaves predictably in fault conditions
ensure that the code adequately
address identified faults
I
T
E
R
A
T
I
O
N
S

## Slide 50: General FMEA Process
The general goal is to develop a list of potential failures as early as possible
General process
  select FMEA strategy
  scope and planning of FMEA
  failure identification
  failure analysis
  resolution of undetected faults and fault handling issues

## Slide 51
Select FMEA Strategy
First decide upon a strategy for performing the overall FMEA
  establish guidelines and completion criteria
    error detection can lead to state explosion
    establish fault thresh hold criteria
  select the analysis approach
    HW, SW, system, mixed

## Slide 52: FMEA Planning
You are essentially planning meetings
Long term planning
  how many meetings will you need to meet your goals and completion criteria
  how will you partition the meetings
    some FMEAs will be dependent upon other FMEA efforts
  what will be the products
    minutes, action items, documentation

## Slide 53: FMEA Planning
Roles
  engineers
    only those involved with the unit analysis
  management
    ensures buy in
  FMEA facilitator
    keeps FMEA on track
Preparatory materials (designs, etc.)

## Slide 54: Failure Identification
Failure Identification Guidance
  faults can be derived from the domain
  faults can be derived from operational scenarios (operational scenarios)
  faults can be derived from knowledge of the system’s internal function and structure
  faults can be derived from an analysis of previous system failures - not proactive

## Slide 55: Failure Identification
Techniques
  structured brainstorming
  interviews
  formal analysis
  some disciplined techniques have evolved
    Joint Application Design (JAD)
    Delphi Technique
    Hazard and Operability Analysis

## Slide 56: General FMEA Process
Failure Analysis
  two basic strategies
    inductive
    deductive
Failure
DEDUCTIVE
How did
this occur?
INDUCTIVE
What will happen
now that the
failure has occurred
How
What

## Slide 57: General FMEA Process
Failure Analysis: Creating Fault Trees
  introduced as a means of visualizing system failures
  based on hardware systems
  typically utilizes a consistent terminology and documentation technique
AND
OR
Terminal
Event
Undeveloped
Event
Resultant
Event

## Slide 58: General FMEA Process
Failure Analysis: Creating Fault Trees
  And Gate: Failure occurs if all input events occur
  Or Gate: Failure occurs if any input events occur
  Terminal Event: Basic failure event needing no further development

## Slide 59: General FMEA Process
Failure Analysis: Creating Fault Trees
  Undeveloped Event: A failure event that may have a root cause but is not developed any further
  Intermediate Event: An event that occurs because of another, or a series of events
The basic elements of a fault tree are gates and events
Biggest part of a FMEA exercise

## Slide 60: Example Fault Tree
Driver
Asleep
Object
Obscured
From View
Driver Didn’t
See Object
Car Fails
to Brake
Brakes
Ineffective
Brakes
Defective
Brakes
Weak
Too
Fast
“Safety Critical Software:Status Report
and Annotated Bibliography”
Place and Kang
Car Hits Object

## Slide 61: General FMEA Process
Criticality Analysis
  each failure is given a criticality ranking
    editorial comment: I prefer simple, low number ratings (i.e. 1-3)
  two approaches with respect to the fault tree
    top level intermediate event rankings
    terminal event ranking

## Slide 62: General FMEA Process
Damage and Effects Analysis
  when a failure occurs, what is the effect to the system and what damage will it suffer
    what are the non-system losses in terms of life, limb, property
    what is the cost of failure
  using the fault tree
    typically analyze top level intermediate failure

## Slide 63: FMEA Table
Putting it all together in a FMEA Table
  the FMEA table provides a tabular listing of the possible system failures and includes their:
    reason, effects, severity, probability of occurrence, probability of detection, corrective/handling actions
See the example table on page 20 of “Safety Critical Software:Status Report and Annotated Bibliography” ~ Place and Kang

## Slide 64: Example FMEA Table

## Slide 65: FMEA in Practice
NASA Mars Microprobe SW FMEA process
  first performed a system level fault table which provided a fault analysis baseline
    some faults involved HW, SW, and/or both
  after this analysis it was determined that there were 3 critical software components
    telecommunications, impact, and water detection

## Slide 66: FMEA in Practice
JPL’s findings from the Mars Microprobe Software FMEA
  clarification of sequence and fault response
  clarification of software error variables during an anomalous event
  recommendation of test cases
  identification of software faults that could be avoided altogether

## Slide 67: FMEA in Practice
JPL’s findings from the Mars Microprobe Software FMEA (continued)
  risk driven
  allows iteration and refocusing on emerging software failure issues as the software is built and tested
  provided a relationship between risk and failure

## Slide 68: FMEA in Practice
An emerging philosophy is to take a systems approach using complimentary and redundant HW and SW safety techniques
  graceful degradation, proactive failure detection, and fail safe as a system engineering issue
An example is the Boeing 777 aircraft
  fly-by-wire avionics with minimal mechanical backup should the primary automated system fail

## Slide 69: FMEA in Practice
With the emergence and importance of transaction based system, concerns arise
  ACID principles
  transaction management
  reliability
  correctness
  performance
  graceful degradation
  security

## Slide 70: All that having been said...
Risk and opportunity go hand-in-hand:
“The greatest rewards go to those that assume the greatest risk”
“The only failure is not taking a chance to fail”
“Risk is essential to progress”
It is essential to balance the negative consequences of risk against the potential benefits in a deliberate and disciplined way

## Slide 71: Summary
Risk is an inherent part of software development
  often ignored or at best dealt with in an ad-hoc way
Risk can be managed
  assess
  analyze
  track
  control

## Slide 72: Summary
Operational Risks and FMEA
  while overlooked in many web based systems, risk management is getting more attention with the emergence of:
    malicious pranksters (viruses)
    personal information compromise
    electronic commerce
    electronic government
    information warfare

## Slide 73: Questions

## Slide 74: Summary
Operational risks are a part of reality
Operational risks can be identified, but the system may or may not handle all failure modes
Failure Mode Effects Analysis is a disciplined method for identifying system failures
  helps in developing mitigating strategies
  helps define graceful degradation
  helps in system test